## Лист1
| Demo Web Shop |  |  | Introduction: |  |  | Our project is web aplication with a diverse range of products. We offer books, computers, electronics, jewelry, clothing, shoes, and music albums
| First stage completion date | 2023-07-16 |  | Objective: |  |  | The testing objective is to ensure the functionality and user experience of the online platform meet high standards for convenient and enjoyable shopping.This includes verifying the responsivenees and usability of the interface, testing various purchasing scenarios to validate fast and accurate order processing. When conducting testing, we aim to provide a flawless user interface.
| End of the project | 2023-08-16 |  | Principles: |  |  | To the optimal amount of documentation, to prevent bugs.
| In Scope | Entry Conditions (for test execution) |  | People
1 | Usability testing of the user interface. | 1 | There is an entry point (API or GUI) for the application and the editor | Testers: |  | Tokarchuk Anna
2 | Test Shopping Cart Functionality | 2 | No known blocking bugs | Test Environment
|  | Exit conditions (for test execusion) |  | It is expected that the majority of users will be working in Windows-systems and browsers - Google Chrome, Opera
3 | Testing the functionality of purchasing products | 1 | All included in the test plan is completed | Timescales (each iteration)
|  | 2 | No high-priority critical bugs found | 1 | Planning | 2 days
4 | Testing the functionality delivery mechanisms | 3 | Low-priority bugs do not impact the main workflow scenario | 2 | Checklist and test case development | 2 days
5 | Testing the functionality of payment | Risks |  | 3 | Test execution | 2 days
| Out of scope | 1 | Poorly designed architecture | 4 | report | 2 days
1 | Automation for all test cases across all types of testing | 2 | Incorrect/Changing priorities
2 | No regression testing | 3 | Unavailability/Absence of testing environments